## Read Me
Obsidian Group Change Data Pack
Fictional input data for ChangeTools infrastructure candidate assessment
Purpose | This workbook contains KPI, risk, stakeholder, and communications data for a digital-first retail change programme.
Important note | Data is intentionally imperfect. Candidates should demonstrate robust ingestion, data validation, storage, observability, and clear handling of missing/ambiguous values.
Company | Obsidian Group
Programme | Hybrid digital-first retail operating model
Fictional data | Yes. Do not treat as real company information.

## KPI Tracker
KPI Tracker
Weekly regional metrics used by leadership to assess adoption and change performance
Week Starting | Region | Digital Workflow Adoption % | Training Completion % | Employee Sentiment % | Avg Support Handling Time (mins) | Weekly Report Submitted | Manual Reporting Hours | Data Quality Flag | Notes
2026-03-02 | North | 42% | 58% | 64% | 14 | Yes | 22 | OK
2026-03-02 | South | 55% | 76% | 74% | 11.9 | Yes | 15 | OK
2026-03-02 | East | 65% | 82% | 78% | 10.7 | Yes | 11 | OK
2026-03-02 | West | 36% | 49% | 55% | 14.4 | Yes | 26 | OK
2026-03-09 | North | 46% | 61% | 65% | 13.7 | Yes | 20.8 | OK
2026-03-09 | South | 59% | 79% | 75% | 11.6 | Yes | 13.8 | OK
2026-03-09 | East | 69% | 85% | 79% | 10.3 | Yes | 9.8 | OK
2026-03-09 | West | 42% | 52% | 56% | 14.1 | No | 24.8 | OK
2026-03-16 | North | 50% | 64% | 66% | 13.3 | Yes | 19.6 | Check definitions
2026-03-16 | South | 63% | 82% | 76% | 11.2 | Yes | 12.6 | OK
2026-03-16 | East | 73% | 88% | 80% | 10 | Yes | 8.6 | OK
2026-03-16 | West | 46% | 55% | 57% | 13.7 | Yes | 23.6 | Check definitions
2026-03-23 | North | 54% | 67% | 67% | 12.9 | Yes | 18.4 | OK
2026-03-23 | South | 67% | 85% | 77% | 10.9 | Yes | 11.4 | OK
2026-03-23 | East | 77% | 91% | 81% | 9.6 | Yes | 7.4 | OK
2026-03-23 | West | 48% | 58% | 58% | 13.4 | Yes | 22.4 | OK | Manager engagement low
2026-03-30 | North | 58% | 70% | 68% | 12.6 | Yes | 17.2 | OK
2026-03-30 | South | 71% | 88% | 78% | 10.5 | Yes | 10.2 | OK
2026-03-30 | East | 81% | 94% | 82% | 9.4 | Yes | 7 | OK | Pilot team above target
2026-03-30 | West | 54% | 61% | 59% | 13 | Yes | 21.2 | OK | Manager engagement low
2026-04-06 | North | 62% | 73% | 69% | 12.2 | Yes | 16 | Check definitions
2026-04-06 | South | 75% | 91% | 79% | 10.2 | Yes | 9 | OK
2026-04-06 | East | 85% | 96% | 83% | 9.4 | Yes | 7 | OK | Pilot team above target
2026-04-06 | West | 58% | 64% | 60% | 12.7 | No | 20 | Check definitions | Manager engagement low
2026-04-13 | North | 66% | 76% | 70% | 11.9 | Yes | 14.8 | OK
2026-04-13 | South | 79% | 94% | 80% | 9.8 | Yes | 7.8 | OK
2026-04-13 | East | 88% | 96% | 83% | 9.4 | Yes | 7 | OK | Pilot team above target
2026-04-13 | West | 60% | 67% | 61% | 12.3 | Yes | 18.8 | OK | Manager engagement low
2026-04-20 | North | 70% | 79% | 71% | 11.6 | Yes | 13.6 | OK
2026-04-20 | South | 83% | 96% | 81% | 9.5 | Yes | 7 | OK
2026-04-20 | East | 88% | 96% | 83% | 9.4 | Yes | 7 | OK | Pilot team above target
2026-04-20 | West | 66% | 70% | 62% | 12 | Yes | 17.6 | OK | Manager engagement low

## Risk Register
Risk Register
Risks identified across communications, adoption, data quality, and governance
Risk ID | Risk | Category | Severity | Probability | Impact | Owner | Status | Mitigation | Evidence / Trigger
R-01 | Middle management resistance | Adoption | High | High | High | Transformation Lead | Open | Target manager enablement sessions and weekly blocker reviews | Lower adoption in West/North where manager engagement is low
R-02 | Job security concerns in customer service | People | High | Medium | High | HR Director | Open | FAQs and retraining narrative before next communication | Call notes mention automation concerns and job security
R-03 | Inconsistent regional messaging | Communications | Medium | High | Medium | Comms Lead | Open | Single communication pack and approved talking points | Regions are creating separate decks
R-04 | Reporting definitions not standardised | Data | Medium | Medium | High | COO Office | In progress | Define adoption, active usage, and reporting completion once | Data quality flags in KPI sheet
R-05 | Rollout timeline uncertainty | Governance | Medium | Medium | Medium | Regional Ops | Open | Publish milestone map and decision log | Different comments mention June and July
R-06 | Low training completion before mandatory rollout | Readiness | High | Medium | High | Transformation Lead | In progress | Escalate regions below 80% training completion | North and West lag behind in early metrics

## Stakeholders
Stakeholder Map
Audience-specific concerns and communication needs
Stakeholder Group | Scope | Influence | Current Sentiment | Primary Concern | Recommended Message | Preferred Channel | Cadence | Evidence Source
Executive leadership | Company-wide | High | Neutral | Visibility of blockers and adoption | Weekly progress view will show adoption, blockers, and escalation needs | Dashboard + weekly email | Weekly | Call notes, leadership update
Regional managers | Regional | High | Mixed | Control over local rollout plans | Regional plans will keep local nuance while using one version of the programme story | Regional workshops | Bi-weekly | Stakeholder feedback
Store managers | Store-level | High | Concerned | Timeline clarity and mandatory dates | The rollout will be phased with clear milestones, training, and escalation support | Manager pack + huddles | Weekly during rollout | Call notes
Customer service teams | Function | Medium | Anxious | Role changes and automation | The programme reduces repetitive work and includes retraining and support | FAQs + team briefings | Bi-weekly | HR comments
Digital transformation team | Programme | Medium | Positive | Slow adoption in regions with weak manager engagement | Manager engagement will be tracked and acted on as a key adoption driver | Working sessions | Weekly | Transformation notes
Store associates | Store-level | Low | Unclear | How daily work changes | Practical guides will show what changes, what stays the same, and where to get help | Store briefings | Monthly | Assumption based on rollout needs

## Comms Calendar
Communications Calendar
Draft plan for programme narrative and stakeholder enablement
Date | Audience | Channel | Message Theme | Owner | Status | Dependency | Notes
2026-04-24 | Regional managers | Workshop | Rollout milestones and manager role | Comms Lead | Draft | Validated timeline | Must resolve June/July ambiguity
2026-04-25 | Customer service teams | FAQ + briefing | Role impact, retraining, support | HR Director | Draft | HR sign-off | Tone must avoid cost-cutting framing
2026-04-29 | Store managers | Manager pack | What changes, when, and how to escalate | Transformation Lead | Not started | Regional date confirmation | Include talking points
2026-05-03 | Executive leadership | Dashboard email | Adoption, sentiment, blockers | COO Office | In progress | KPI definitions | Need one view by region
2026-05-08 | All employees | Townhall | Customer experience and digital-first model | CEO Office | Not started | Narrative approval | Reinforce not a headcount message
2026-05-15 | Digital transformation team | Working session | Data quality and reporting standards | Transformation Lead | Not started | Dashboard fields | Define adoption and active usage

## Data Dictionary
Data Dictionary
Definitions candidates should preserve or validate during ingestion
Field | Definition | Known Issue / Validation Rule
Digital Workflow Adoption % | Percentage of target users who used the new workflow at least once during the measured week. | Definition may not equal active usage. Flag if unclear.
Training Completion % | Percentage of target users who completed required digital workflow training. | Target above 90% mentioned but not formally confirmed.
Employee Sentiment % | Positive or neutral responses from pulse checks. | Survey sample size not included.
Avg Support Handling Time | Average handling time for customer support cases in minutes. | Target is 20% reduction, baseline must be confirmed.
Weekly Report Submitted | Whether the regional team submitted the weekly report. | No does not necessarily mean no activity occurred.
Manual Reporting Hours | Estimated weekly hours spent on manual reporting. | Self-reported. Treat as approximate.