# AI Call Notes: Digital-First Change Programme Discovery

Obsidian Group | Strategy, communications, and measurement workstream

| Meeting date | 17 April 2026 |
| --- | --- |
| Meeting length | 58 minutes |
| Source | Auto-generated notes from video call recording |
| Purpose | Clarify priorities, risks, stakeholder concerns, and measurement needs for the digital-first retail operating model. |
| Attendees | Amelia Hart, CEO; Marcus Reed, COO; Sana Patel, HR Director; Liam O’Connor, Transformation Lead; Priya Shah, Regional Operations; Elena Brooks, Change Communications; Theo Martin, ChangeTools observer. |
| AI confidence | Medium-high. Speaker attribution may be imperfect. Several comments about rollout timing and job impact require confirmation. |

# 1. Executive summary

Obsidian Group is moving from a regionally inconsistent store-led model to a hybrid digital-first operating model. Leadership wants the programme to be positioned around customer experience, better visibility, and reduced manual work rather than cost-cutting. The most important risks discussed were regional manager resistance, unclear timelines for store managers, job security concerns in customer service, and inconsistent communication between regions.

# 2. Key themes captured by the AI note taker

| Theme | Notes |
| --- | --- |
| Customer experience narrative | CEO emphasized that all messaging should frame the programme as a service-quality and customer journey improvement, not as a headcount reduction initiative. |
| Operational visibility | COO wants weekly adoption reporting by region, with a clear view of blockers, training completion, and support handling time. |
| Manager enablement | Regional and store managers need a practical rollout pack, FAQs, talking points, and a clear escalation path. |
| Data quality challenge | Weekly reporting is currently manual and inconsistent; teams use different templates and definitions. |
| Adoption risk | Early pilot data suggests lower adoption where middle managers are not actively reinforcing the workflow. |

# 3. Speaker notes and transcript-style excerpts

Amelia Hart, CEO: “We need this to feel like a customer experience programme. If people hear automation and assume cuts, we will lose trust before we start.”

Marcus Reed, COO: “I do not want another reporting layer that arrives late and is impossible to compare. I need a weekly view by region and a simple way to spot blockers.”

Sana Patel, HR Director: “Customer service teams are nervous. Any communication must be sensitive around role changes and must explain what support and retraining will be available.”

Priya Shah, Regional Operations: “Managers keep asking when the new workflow becomes mandatory. Some regions are already moving. Others are waiting because they think the plan might change.”

Elena Brooks, Change Communications: “We need one version of the story. Right now every region is creating its own deck and the message is drifting.”

Liam O’Connor, Transformation Lead: “Pilot adoption is promising where managers are engaged, but training completion is behind in the North and West regions.”

# 4. Decisions and working assumptions

Programme narrative will focus on customer experience, consistency, and reducing repetitive manual work.

A weekly change dashboard will be created for executives and regional leaders.

Store managers will receive a manager enablement pack before the next regional rollout wave.

Customer service communications will include a clear statement on role impact, retraining, and support.

Regional rollout will remain phased, but leadership wants a single source of truth for timeline and adoption status.

# 5. Risks and concerns raised

| ID | Risk | Severity | AI-captured rationale |
| --- | --- | --- | --- |
| R-01 | Middle management resistance | High | Managers in lower-adoption regions may delay or dilute the rollout if they are not confident in the programme. |
| R-02 | Job security concerns | High | Customer service teams may interpret automation as a headcount reduction programme. |
| R-03 | Inconsistent regional messaging | Medium | Different decks and informal explanations are creating confusion and message drift. |
| R-04 | Weak reporting consistency | Medium | Adoption reporting uses different definitions across regions, reducing leadership trust in the data. |
| R-05 | Timeline uncertainty | Medium | Store managers do not know which milestones are fixed and which are still subject to change. |

# 6. Metrics discussed

Digital workflow adoption target: 80% within 6 months.

Customer support handling time reduction target: 20%.

Employee sentiment target: above 70% positive/neutral sentiment.

Manual reporting effort reduction target: 30%.

Weekly reporting completion target: 100% of regional teams by the end of the quarter.

Training completion target was discussed as “above 90% before mandatory rollout”, but final target needs confirmation.

# 7. Action items

| ID | Owner | Action | Due | Status |
| --- | --- | --- | --- | --- |
| A-01 | Elena Brooks | Create a single programme narrative and communication pack. | 24 April 2026 | Open |
| A-02 | Liam O’Connor | Define weekly adoption dashboard fields and required data owners. | 22 April 2026 | Open |
| A-03 | Sana Patel | Draft employee-facing FAQs covering role impact and retraining support. | 25 April 2026 | Open |
| A-04 | Priya Shah | Validate regional rollout dates with each regional director. | 29 April 2026 | Open |
| A-05 | Marcus Reed | Confirm executive dashboard cadence and escalation thresholds. | 30 April 2026 | Open |

# 8. Open questions and AI uncertainty flags

Exact launch date for the mandatory workflow appears unresolved. Notes mention June and July in different contexts.

AI notes captured “training completion above 90%” but this may be an aspiration rather than an approved KPI.

It is unclear whether customer support headcount changes are out of scope or simply not yet communicated.

Regional ownership for the dashboard is not fully defined.

Data definitions for adoption, active usage, and reporting completion need to be standardised.

# 9. Candidate test note

This is fictional mock data for a technical assessment. The content intentionally includes structured facts, ambiguous statements, risks, action items, and inconsistent notes so that an AI infrastructure prototype can demonstrate ingestion, processing, storage, traceability, and error handling.